# Updated Experimental Plan

Camera-first, sensor-agnostic, minimum-scope path with Quest as optional validation

Course Project Working Plan

# 1. Updated Strategy

The core research question remains manipulation-intent representation, but sensing is now explicitly separated from the algorithm. The project must remain complete even if Meta Quest 3 cannot be borrowed.

Camera / Public Data / Optional Quest → Standardized Palm-Local Hand Pose → Intent Representation → Dexterous PPO

# 2. Design Principles

VR is not a dependency. Camera input is the primary practical front-end; Quest becomes optional validation.

Do not turn the project into a hand-pose-estimation project: use an off-the-shelf tracker.

Do not track the real cube in the MVP. A physical cube may be used only as a prop to induce natural hand shapes.

The algorithm begins from a standardized palm-local hand pose, making the sensing front-end replaceable.

Use the GPU cluster continuously for full-run validation; use the laptop for coding, visualization, and smoke tests.

# 3. Fixed Core Platform

| Component | Choice |
| --- | --- |
| Simulator | Isaac Lab 5.1 |
| Robot | 16-DoF Allegro Hand |
| Task | Cube reorientation / existing Direct RL environment |
| Controller | PPO |
| Common state | Robot state + simulator object state + object goal |
| Action | 16-D Allegro joint action |

# 4. Sensing Front-End

| Priority | Source | Purpose |
| --- | --- | --- |
| Primary | RGB/RGB-D camera + off-the-shelf hand tracker | Generate hand skeleton without depending on Quest availability |
| Fallback | Public hand-motion dataset | Keep project moving if live camera tracking is delayed |
| Optional | Meta Quest 3 hand tracking | Sensor validation / demo using the same standardized interface |

All sources should be converted to the same representation before entering the experiment. The intended interface is a sequence of palm pose plus hand landmarks/joints.

# 5. Palm-Local Normalization

For each hand point p_i, remove global translation and wrist orientation using:  p_tilde_i = R_palm^-1 (p_i - p_palm).  This preserves hand shape and coordination while discarding global hand motion that the fixed-palm Allegro task cannot execute.

This deliberately removes real cube ↔ sim cube calibration from the MVP. The study therefore concerns hand-configuration-based manipulation intent, not full object-centric contact geometry.

# 6. Core Experimental Conditions — Reduced MVP

| Priority | Condition | Representation | Status |
| --- | --- | --- | --- |
| 1 | Object-only | No human signal | Mandatory |
| 2 | Fingertip Geometry | Palm-local fingertip coordinates | Mandatory |
| 3 | PCA Synergy | PCA latent from palm-local full hand; k=4 | Core method |
| 4 | Full Hand | Full palm-local hand vector | Optional strengthening baseline |

The minimum viable study is therefore a three-way comparison: Object-only → Fingertips → PCA-4. Full Hand is added only after the core hypothesis is testable.

# 7. Data Collection — Minimum-Effort Path

Save raw hand skeleton data once: timestamp, palm pose, and all available landmarks/joints.

Use a physical cube as an untracked prop if helpful for natural grasping and finger coordination.

Derive Fingertips, PCA-4, PCA-2/8, and Full Hand offline from the same raw recording.

Avoid AprilTag, real-cube pose estimation, cross-device calibration, and synchronization in the MVP.

If Quest becomes available later, map its hand skeleton into the same palm-local representation and reuse the downstream pipeline unchanged.

# 8. Experiment Sequence and Go/No-Go Decisions

| Checkpoint | Experiment | Decision |
| --- | --- | --- |
| End W2 | Full Object-only baseline | If task is already at ceiling, modify task so intermediate intent can express strategy/subgoal rather than only final goal. |
| End W5 | Object-only vs Fingertips | If no difference, inspect task formulation before investing in synergy or more sensing. |
| End W6 | Fingertips vs PCA-4 | If PCA-4 approaches Fingertips, core compression story is viable. |
| After core result | Add Full Hand / one ablation / Quest | Only strengthen the study after the MVP works. |

# 9. Evaluation

Primary: Success Rate (SR).

Primary: sample efficiency, e.g. N80.

Primary: learning-curve AUC.

Secondary: final orientation error and representation dimension.

Optional: one of PCA dimension ablation or tracking-noise robustness.

Use identical training budgets and evaluation episodes across conditions; report mean and uncertainty across seeds.

# 10. Updated 12-Week Timeline

| Week | Learning / Engineering | Experiment / Deliverable |
| --- | --- | --- |
| 1 | PPO / GAE; read Allegro environment | Understand observation, action, reward and reset |
| 2 | Dexterous manipulation fundamentals | Cluster: full Object-only baseline; evaluate ceiling |
| 3 | Hand-pose representations | Camera + off-the-shelf tracker; stable raw hand skeleton |
| 4 | PCA / hand synergy | Palm normalization; derive Fingertips and PCA features |
| 5 | Conditioned RL | Fingertip PPO; cluster full run; early RQ1 test |
| 6 | — | PCA-4 PPO; 3-way pilot; core hypothesis decision |
| 7 | Statistics / experiment hygiene | 3 seeds × 3 methods; freeze setup |
| 8 | — | 5-seed main experiment on cluster |
| 9 | — | Optional Full Hand baseline if useful |
| 10 | — | One ablation: PCA k={2,4,8} OR tracking noise |
| 11 | — | Quest validation if available; otherwise strengthen camera/offline results |
| 12 | — | Analysis, plots, report, demo/presentation |

# 11. Compute Workflow

Laptop RTX 3070 Ti: code development, GUI/visual checks, smoke tests, local single-seed pilots.

School GPU cluster: run a full training job as soon as each method works locally; do not wait until late project weeks.

Main multi-seed results should be generated on the cluster for speed and reproducibility.

# 12. Scope Ladder

| Level | Deliverable |
| --- | --- |
| MVP — must finish | Object-only + Fingertips + PCA-4, using camera or offline hand data, 3–5 seeds |
| Should finish | Full Hand high-information baseline |
| Optional extension | One PCA-dimension or noise-robustness ablation |
| Bonus | Quest 3 validation using the same standardized hand-pose interface |

# 13. Updated Claim Boundary

The MVP should claim evidence about hand-configuration-based manipulation intent for a fixed-palm dexterous controller. It should not claim full human-object interaction intent, contact-aware teleoperation, or object-centric real-to-sim transfer unless real object tracking is later added.